## Slide 1: GYM MANAGEMENT SYSTEM
MINI PROJECT
Department of MCA, MES College of Engineering , Kuttippuram
25th OCTOBER 2023
PREPARED BY
MUHAMMED FAYIZ K (MES22MCA-2037)

## Slide 2: GUIDED BY Mr.MOHAMMED JABIR C ASSISTANT PROFESSOR MASTER OF COMPUTER APPLICATIONS MES COLLEGE OF ENGINEERING , KUTTIPPURAM

## Slide 3: Introduction Modules Product Backlog User Story Project Plan Sprint Data Flow Diagram Devoloping Environment
CONTENTS

## Slide 4
INTRODUCTION
In many Gyms, the payment receipts are in paper format. So it is very difficult for both gym members to keep all the paper receipts safely and to gym trainer to keep reminding for the fee receipts. Sometimes it creates a trouble when members lost their receipts. The other problem that can be faced by a gym owner is that if he/she wants to inform any message related to working or nonworking days of gym, manually sending message become difficult. If there is online application available these problems can be solved. So, I am developing an android or web application to overcome some of these issues. So this project can be helpful for both gym owner as well as for gym members. In this application all receipts are store in a digital format, so there are no issues of loosing any confidencial receipts. This application will also notify the user (gym members) about their fees and also notifies the gym owner about the payment clearence. This application in future can be elaborated by providing supplement store , diet information, personal training etc.

## Slide 5
MODULES
ADMIN
  LOGIN
  MANAGE USERS
  CREATE/MANAGE BILL DETAILS
  MANAGE STAFF
  MANAGE SUPPLEMENT STORE
USERS
  REGISTER
  LOGIN
  VIEW DETAILS
  SEARCH RECORDS
TRAINER
  LOGIN
  REGISTER
  MANAGE DIET
  VIEW USERS

## Slide 6
ID | PRIORITY | SIZE (Hours) | SPRINT | STATUS | NAME
1 | Medium | 8 | 1 | Planned | Registration
2 | Medium | 4 |  | Planned | Login
3 | High | 10 | 2 | Planned | Table Design
4 | High | 9 |  | Planned | Coding
5 | Medium | 4 | 3 | Planned | Testing data
6 | High | 6 |  | Planned | Output generation
PRODUCT BACKLOG

## Slide 7
USER STORY
I want to
User Story ID | As a <type of user> | I want to | So that I can
1 | Admin | Login | Registered successfully with credentials
2 | Admin | Login | Login successfully with valid credentials
3 | Admin | Create/manage bill details | Create and manage bill details of gym fee
4 | Admin | Manage customer | Add/block customers
5 | Admin | Manage diet | Add/edit diet plans
6 | Admin | Manage supplement store | Add/edit supplement products
7 | User | Register | Registered successfully with credentials
8 | User | Login | Login successfully with valid credentials
9 | User | View details | View bill details
10 | User | Search records | Search for bill details

## Slide 8
PROJECT PLAN
User Story ID | Sprint | Start Date | End Date | Day | Status
01 ,06, 07 | Sprint 1 | 15/09/2023 | 25/09/2023 | 10 | Planned
08, 09 |  | 26/09/2023 | 12/10/2023 | 10 | Planned
10,11,12 | Sprint 2 | 13/10/2023 | 25/10/2023 | 12 | Planned
05,13,15 |  | 26/10/2022 | 03/11/2023 | 08 | Planned
02,03 | Sprint 3 | 08/11/2023 | 16/11/2023 | 08 | Planned
04,14 |  | 17/11/2023 | 30/11/2023 | 13 | Planned

## Slide 9
Backlog Item | Compl-etion Date | Original Estimate | Day 1 15/09 | Day 2 20/09 | Day 3 21/09 | Day 4 28/09 | Day 5 29/09 | Day 6 04/10 | Day 7 05/10 | Day 8 06/10 | Day 9 11/10 | Day10 12/10
User Story # 1 |  | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS
Form Design | 15/09 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table Design | 28/09 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 06/10 | 6 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 0 | 0
Testing & validation | 12/10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Total |  | 13 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1
SPRINT PLAN 1

## Slide 10
PROJECT PLAN
Backlog Item | Compl-etion Date | Original Estimate | Day 1 13/10 | Day 2 18/10 | Day 3 19/10 | Day 4 20/10 | Day 5 25/10 | Day 6 26/10 | Day 7 27/10 | Day 8 01/11 | Day 9 02/11 | Day10 03/11
User Story # 2 |  | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS
Form Design | 13/10 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table Design | 18/10 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 01/11 | 8 | 0 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 0
Testing & validation | 03/11 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Total |  | 14 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2
SPRINT PLAN 2

## Slide 11
Backlog Item | Compl-etion Date | Original Estimate | Day 1 08/11 | Day 2 09/11 | Day 3 10/11 | Day 4 15/11 | Day 5 16/11 | Day 6 17/11 | Day 7 22/11 | Day 8 23/11 | Day 9 24/11 | Day 10 29/11 | Day11 30/11
User Story # 3 |  | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS
Coding | 22/11 | 9 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0
Testing & validation | 30/11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1
Total |  | 14 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1
SPRINT PLAN 3

## Slide 12: Data Flow Diagram
Admin
User
Gym Management System
Database
Level 0

## Slide 13: Data Flow Diagram
Admin
Register
Login
Manage supplement store
Manage Diet
Create/Manage bill details
Manage customer
Admin
Login
Bill
Customer
Diet
Store
Level 1.1

## Slide 14: Data Flow Diagram
User
Register
Login
View details
Search Records
User
Login
Bill
Bill
Level 1.2

## Slide 15
DEVELOPMENT ENVIRONMENT
SOFTWARE SPECIFICATION
Operating System
Frond End
Framework
Backend
IDE
: Windows 7 or above
: Html, Css
: Laravel
:Php,MySQL
: Visual Studio Code
HARDWARE SPECIFICATION
Processor
Hard Disk
RAM
: Intel i3 or above
: 256 SSD
: 4GB or Above